## Sheet1
ADP # | Name of Scheme | Total Estimate | Expenditure durning Previous Years | Allocation during CFY (Original) | Release during Current Financial Year | Expenditure during Current Financial Year | % age Untilization against releases | Progress Expenditure | Target achieved upto LFY 2017-18 | Target for CFY 2018-19 | Acheid Current Financial Year 2017-18 | Total achied: | year of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
AGRICULTURE EXTENSION
06 | 170309-Promotion of Agriculture Activities in SWA (B) | 33.29 | 0 | 33.29 | 8.479 | 0 | 0% | 0 | 0% | 100% | 0% | 0% | June 2020
13 | 180102-Sustanable Development of Agriculture in District SW (A)/DDWP/ 22-04-2019 | 45 | 0 | 45 | 11.461 | 0 | 0% | 0 | 0% | 100% | 0% | 0% | June 2020
AGRICULTURE LIVESTOCK & DD |  | 78.29 | 0 | 78.29
67 | 180070-Reconstruction of Assistant Director Office and Solarization of Vaccine Bank and Construction vety: Health Facilities in District SW (B) | 45.622 | 0 | 7.745 | 0 | 0 | #DIV/0! | 0 | 0% | 16.98% | 0% | 0% | Beyond June 2020 | Scheme approved in PDWP held on 22/04/2019
71 | 140293- Construction of Buildings for 07 Existing CVCs and CVDs in Closed area, SWA (A)/FDWP/19.04.2017 | 25.104 | 12.5 | 7.604 | 0 | 0 | #DIV/0! | 12.5 | 49.79% | 30.29% | 0% | 49.79% | Beyond June 2020 | Work in progress wihle 01 unit Work yet Not started
75 | 010076-Opening 41 No. Veterinary Centers, 22 AICs and Up-gradation of 01 CVD to CVH Status in SWA ® | 294.597 | 279.597 | 15 | 0 | 0 | #DIV/0! | 279.597 | 94.91% | 5.092% | 0% | 94.91% | Beyond June 2020
76 | 070082- Construction of Building for 06 existing CVDs in SWA. (A) ADSC /08.04.2013 | 22.005 | 18.675 | 3.03 | 0 | 0 | #DIV/0! | 18.675 | 84.87% | 13.77% | 0% | 84.87% | Beyond June 2020
93 | 150157- Establishment of Mobile Veterinary Clinic in SWA (A)/FDWP/03.11.2015 | 42.121 | 32.335 | 9.786 | 0 | 0 | #DIV/0! | 32.335 | 76.77% | 23.23% | 0% | 76.77% | Beyond June 2020
TOTAL ONGOING SCHEMES LIVESTCOK |  | 429.449 | 343.107 | 43.165 | 0 | 0 | 0% | 343.107 | 79.89% | 10.05% | 0% | 79.89%
GRANT TOTAL OF AGRICULTURES |  | 507.739 | 343.107 | 121.455 | 0 | 0 | 0% | 343.107 | 67.58% | 23.92% | 0% | 67.58%
BUILDING DISTRICT PROGRAM
155 | 180099-Construction / Improvement & Rehabilitation Tehsil offices & Construction of Rest Houses in District SW (B) | 40.236 | 0 | 40.236 | 0 | 0 | 0% | 0 | 0% | 100% | 0% | 0% | June-2020
156 | 180100-Construction of Levies / Khassadar Barracks & Levy Line in District SW (B) | 30.043 | 0 | 30.043 | 0 | 0 | 0% | 0 | 0% | 100% | 0% | 0% | Beyond June 2020
167 | 180503-Rehabilitation of Tribal District Administration Buildings and residences and provision of missing facilities in District SW (B) | 34.265 | 0 | 20.16 | 0 | 0 | #DIV/0! | 0 | 0% | 58.84% | 0% | 0% | Beyond June 2020
170 | 160050-Rehabilitation, Improvement & Additional Work in SWA (A)/FDWP/10.01.2017 | 59.72 | 53.72 | 1 | 0 | 0 | #DIV/0! | 53.72 | 89.95% | 1.674% | 0% | 89.95% | Beyond June 2020
TOTAL ONGOING SCHEMES OF BUILDING DISTRICT PROGRAM |  | 164.264 | 53.72 | 91.439 | 0 | 0 | #DIV/0! | 53.72 | 89.95% | 260.5% | 0% | 89.95%
DWSS (District Program)
191 | 130022- Const: of Solar Based DWSS in SWA. A)FDWP/07-03-2014 | 120.752 | 104.893 | 15.424 | 0 | 0 | #DIV/0! | 104.893 | 86.87% | 12.77% | 0% | 86.87% | Beyond June 2020
197 | 100105-Const: of 9-Nos DWSS tube well based DWSS in SWA (R) (A)/FDWP/ 12-06-2012 | 105.763 | 56.315 | 10.217 | 0 | 0 | #DIV/0! | 56.315 | 53.25% | 9.66% | 0% | 53.25% | Beyond June 2020
200 | 140291- Improvement & Rehabilitaiton of 06 DWSS facilities in South Waziristan (Umbrella) (A)/DDWP 27-05-2019 | 27.003 | 0 | 5.1 | 0 | 0 | 0% | 0 | 0% | 18.89% | 0% | 0% | Beyond June 2020
202 | 110276-Cosntruction of 10 No. DWSS (Tube Well Based) in SWA (A) /FDWP/04.04.2012 | 109.936 | 95.936 | 8.529 | 0 | 0 | 0% | 95.936 | 87.27% | 7.758% | 0% | 87.27% | Beyond June 2020
230 | 170299-Construction of Solar Based DWSS in SWA (A)FDWP 01.01.2018 | 59.98 | 36 | 23.98 | 5.995 | 0 | 0% | 36 | 60.02% | 39.98% | 0% | 60.02% | June 2020
231 | 170300-Construction of Gravity Based DWSS in SWA (A)/FDWP 01.01.2018 | 98.421 | 46 | 12.367 | 0 | 0 | 0% | 46 | 46.74% | 12.57% | 0% | 46.74% | Beyond June 2020
232 | 170301-Rehabilitation & Solarization existing DWSS in District South Waziristan (A)/DDWP/03.04.2019 | 68.16 | 0 | 8.572 | 0 | 0 | 0% | 0 | 0% | #VALUE! | 0% | 0% | Beyond June 2020
236 | 180540-Constrcution of Solar Based / Gravity Based DWSS in District South Waziristan (B) | 110 | 0 | 5.012 | 0 | 0 | 0% | 0 | 0% | 4.556% | 0% | 0% | Beyond June 2020
241 | 140319-Construction of 10 DWSS Tube well based, Construction of 13 DWSS Gravity based and construction of 01 open well in Mehsud closed area. (Umbrella) (B). | 147 | 0 | 5 | 0 | 0 | 0% | 0 | 0% | 3.401% | 0% | 0% | Beyond June 2020
242 | 120008- Const: of DWSS ( Solar Based) in SWA. A)FDWP/ 25.04.2013 | 90.496 | 79.793 | 6.703 | 0 | 0 | 0% | 79.793 | 88.17% | 7.407% | 0% | 88.17% | Beyond June 2020
GANT TOTAL DWSS |  | 937.511 | 418.937 | 92.332 | 5.995 | 0 | 0% | 418.937 | 44.69% | 9.849% | 0% | 44.69%
ELEMENTRY & SECONDARY EDUCATION | [8 empty] | #DIV/0!
301 | 150162- Up-gradation of High Schools to Higher Secondary Status in SWA. (A)/FDWP/10.01.2017 | 141.744 | 84 | 141.744 | 0 | 0 | 0% | 84 | 59.26% | 100% | 0% | 59.26% | Beyond June 2020
302 | 160464-Grant in Aid to HQ 09 Division for Establishment of Cadet Collage Wana (R) | 750.000 | 492.244 | 73.991 | 0 | 0 | 0% | 492.244 | #VALUE! | 0% | 0% | 0% | Beyond June 2020
306 | 170388-Provision of Furniture I the Existing Functional Schools in SWA (B) | 40 | 10 | 1 | 0 | 0 | 0% | 10 | 25% | 2.5% | 0% | 25% | Beyond June 2020
310 | 160491-Grant in Aid to HQ 40 Division for Establishment of Cadet Collage at Sararogha SWA 2018-19 (B) | 820 | 491 | 100 | 0 | 0 | 0% | 491 | 59.88% | 12.2% | 0% | 59.88% | Beyond June 2020
311 | 070129-Estab: of 20-GPS in SW Agency (A)/FDWP/28-02.2013 | 116.729 | 85.156 | 31.573 | 0 | 0 | 0% | 85.156 | 72.95% | 27.05% | 0% | 72.95% | June 2020
312 | 140308- Construction of 15 Addl: Class rooms in Over crowded Schools, Constn: of Buildings for 05 Shelter less Pry Schools & Constn: of Quarters for Existing 10 Functional Girls Schools in Mehsud Closed Area. (Umbrella) (B) | 173 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
319 | 170291-Up-gradation of Primary Level facilities to Middle status in SWA (B) | 120 | 0 | 6 | 0 | 0 | #DIV/0! | 0 | 0% | 5% | 0% | 0% | Beyond June 2020 | The scheme presented in FDWP Meeting held on 01/01/2018 and deffered. DG M&E and Director Education to Assess the feasibility of these schools. Again the scheme on MRS - 2017 has been submitted to District Education Officer, South Waziristan Tribal District
320 | 170292-Up-Gradation of Middle Schools to High Status in SWA (B) | 75 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | 0% | 1.333% | 0% | 0% | Beyond June 2020
321 | 170293-Establishment of Primary Schools (Boys & Girls) in SWA (B) | 125 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
322 | 170294-Solarization and Removal of Deficiencies in Existing Schools in SWA (B) | 80 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | 0% | 1.25% | 0% | 0% | Beyond June 2020
323 | 170295-Establishment of Governor’s Model School Islam – Ud – Din Kot Makin Phase - 11 | 70.755 | 21 | 5.000 | 0 | 0 | 0% | 21 | 29.68% | #VALUE! | #VALUE! | 29.68% | Beyond June 2020
341 | 150167- Rehabilitation & Provision of Furniture to Existing to Existing Educational Facilities in SWA (A)/FDWP/23.02.2016 | 89.997 | 49.324 | 7 | 0 | 0 | 0% | 49.324 | 0% | 0% | 0% | 0% | Beyond June 2020
342 | 150163-Up-gradation of middle Schools to Higher status in SWA. (A)/FDWP/10.01.2017 | 183.996 | 130.22 | 2 | 0 | 0 | 0% | 130.22 | 0% | 0% | 0% | 0% | Beyond June 2020
350 | 150386-Establishment of 16 Primary Schools in SWA (Umbrella) (ADP No.96/140240) (B) | 97.282 | 47 | 1 | 0 | 0 | 0% | 47 | 48.31% | 1.028% | 0% | 48.31% | Beyond June 2020
351 | 150387-Regularization of 06 Community Schools in Closed area SWA (Umbrella) (ADP No.98/140242) (B) | 38.573 | 27.6 | 10.973 | 2.743 | 2.743 | 0% | 30.343 | 71.55% | 28.45% | 25% | 78.66% | June 2020
360 | 110145- Re- Opening of Functional Community Schools in SWA (2016-17) (R) | 137.06 | 97.06 | 40 | 0 | 0 | 0% | 97.06 | 70.82% | 29.18% | 0% | 70.82% | June 2020
361 | 150388-Estab: of 02 Model Schools at Tiarza & Sardar Khan Kot Shaktoi Ladha in Mehsud Closed area SWA (Umbrella) (ADP No.107/140309) (B) | 198.316 | 16.5 | 1 | 0 | 0 | 0% | 16.5 | 8.32% | 0.5042% | 0% | 8.32% | Beyond June 2020
363 | 140313- Up-gradation of 09 Primary Schools to Middle Status and 03 Middle Schools to High Status in Mehsud Closed Area, SWA. (Umbrella) (B) | 140.000 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
364 | 150390-Regularization of 16 No. GFCS Schools in Mehsud area SWA (Umbrella) (ADP No.110/140312) (B) | 191.394 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0.5225% | 1 | 0% | Beyond June 2020
367 | 140288-Up-Gradation 6 Middel School to High Status and Up-Gradation of 03 Primary Schools to Middle Status in District in SW (Umbrella( (B) | 130.64 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0.7655% | 0% | 0% | Beyond June 2020
368 | 070196- Regularization of 50-Community School in SW Agency (A)/FDWP/28-02-2013 | 195.339 | 158.072 | 2.055 | 0 | 0 | 0% | 158.072 | 80.92% | 1.052% | 0% | 80.92% | Beyond June 2020
369 | 080114-Const: of building for 12-Nos Community schools in SW Agency (A)/FDWP/ 28-02-2013 | 78.119 | 67.55 | 10.569 | 0 | 0 | 0% | 67.55 | 86.47% | 13.53% | 0% | 86.47% | June 2019
370 | 140241- Up-Gradation of 9 PS to Middle Status and Up Gradation of 3 Schools from Middle to High Status in District SW (Umbrella) | 113.705 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0.8795% | 0% | 0% | Beyond June 2020
371 | 080116-Provisoin of 06-Nos buildings for shelter less primary schools in SWA (A)/ADSC/ 28-02-2013 | 28.267 | 23.809 | 4.458 | 0 | 0 | 0% | 23.809 | 84.23% | 0% | 0% | 84.23% | June 2020
372 | 090054-Regularization of 16-Nos Communal Schools in SWA (8 Girls & 8 Boys) (A)/FDWP/28-02-2013 | 89.971 | 65.27 | 2 | 0 | 0 | 0% | 65.27 | 72.55% | 2.223% | 0% | 72.55% | Beyond June 2020
374 | 140245-Up- Gradation of 06 Primary Level Facilities to Middle status, 01 Middle Level facility to Height status and rehabilitation of 01 Existing Education Facility in Ladha Sub Division (Closed area) District SW. (B) | 92 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 1.087% | 0% | 0% | Beyond June 2020
375 | 140247-Up-Gradation of 03 Primary Level facilities to Middle Status, 01 Middle School to High Status in Sarwekai Sub Division (Closed area) District SW (B) | 42.554 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 2.35% | 0% | 0% | Beyond June 2020
378 | 150385-Construction of Building for 09 Community Schools, Up-Gradation of 03 P.S to M.S (2 Girls & 2 Boys ) Up-Gradation of 09 P.S to M.S in SWA (Umbrella) (ADP No.95/140235) (B) | 180 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
379 | 150389-Regularization of 07 GMCS and Up-Gradation of 06 Middle Schools to High status in Mehsud area, District SW (Umbrella) ADP No.109/140311 (B) | 155 | 0 | 1 | 0 | 0 | #DIV/0! | 0 | 0% | 0% | 0% | 0% | Beyond June 2020 | Umbrella
380 | 120001- Establishment of Primary level Educational facilities SWA. (A)/ FDWP/16.02.2017 | 173.229 | 134.931 | 1 | 0 | 0 | 0% | 134.931 | 77.89% | 0.5773% | 0% | 77.89% | Beyond June 2020
381 | 120002- Up-gradation from Primary to Middle Schools in SWA. (A)/ FDWP/30.05.2013 | 43.100 | 40.937 | 2.163 | 0 | 0 | 0% | 40.937 | 0% | 0% | 0% | 0% | June 2020
384 | 090052-Upgradation of 04-Nos Primary Schools to Middle status in SWA (02 Girls & 2 Boys) (A)/FDWP/ 28-02-2013 | 45.826 | 31.955 | 13.871 | 0 | 0 | 0% | 31.955 | 69.73% | 30.27% | 0% | 69.73% | June 2020
387 | 160035-Removal of deficiencies in Governor’s Model School in SWA (A)/FDWP/10.01.2017 | 55.463 | 39.143 | 6.32 | 0 | 0 | 0% | 39.143 | 70.57% | 11.39% | 0% | 70.57% | Beyond June 2020
388 | 150384-Establishment of 19 No. Primary Level Education Facilities in SWA (Umbrella) (ADP No.94/140194) (B) | 175.05 | 0 | 1 | 0 | 0 | 0% | 0 | 0% | 0.5713% | 0% | 0% | Beyond June 2020
391 | 140310- Up-gradation of 12 Primary Schools to Middle level in Mehsud Closed Area SWA (Umbrella) (B) | 134.649 | 73.5 | 2 | 0 | 0 | 0% | 73.5 | 0% | 0% | 0% | 0% | Beyond June 2020
394 | 070198-Upgradation of 04-Nos Middle Schools to High status in SWA (A)/FDWP/28-02-2013 | 70.432 | 53.634 | 9.945 | 0 | 0 | 0% | 53.634 | 0% | 14.12% | 0% | 0% | Beyond June 2020
TOTAL ELEMENTRY & SECONDARY EDUCATION ON-GOING |  | 4050.448 | 2239.905 | 479.204 | 2.743 | 2.743 | 0% | 2242.648 | 0% | 11.83% | 0.5724% | 0%
ENERGY & POWER | [7 empty] | 0
410 | 180510-Rehabiliation, Maintance & repair of existing power supply lines / transformers and provision of power transformers in District South Waziristan (B). | 63 | 0 | 63 | 0 | 0 | 0% | 0 | 0% | 100% | 0% | 0% | June - 2020
GRANT TOTAL ENERGY & POWER |  | 63 | 0 | 63 | 0 | 0 | 0% | 0 | 0% | 100% | 0% | 0%
FORESTRY | [7 empty] | 0
423 | 080136-Raising of Fuel Wood Species Plantation in SW Agency (R) (A)/FDWP/09.05.2014 | 160.172 | 153.272 | 6.9 | 1.757 | 0 | 0% | 153.272 | 95.69% | 4.308% | 0% | 95.69% | June 2020
425 | 090063-Development of Carbon Sink through Forestry in SW Agency (R) (A)/FDWP/09-05-2014 | 190.265 | 188.279 | 1.986 | 0.506 | 0 | 0% | 188.279 | 98.96% | 1.044% | 0% | 98.96% | June 2020
432 | 180057-Mitigation of Climate Change effect through raising of plantation in District SW (B) | 80 | 0 | 20 | 0 | 0 | 0% | 0 | 0% | 25% | 0% | 0% | Beyond June 2020
436 | 180277-Livelihood Improvement through NTFP activities in District SW (B) | 20 | 0 | 5 | 0 | 0 | 0% | 0 | 0% | 25% | 0% | 0% | Beyond June 2020
467 | 170312-Afforestiation / Fruit Tree / Plantation in SWA (A)/FDWP/20.09.2017 | 45.366 | 25.622 | 10 | 0 | 0 | 0% | 25.622 | 56.48% | 22.04% | 0% | 56.48% | Beyond June 2020
472 | 170411-Promotion of NTFP Activities in SWA (A)/FDWP/20.09.2017 | 36 | 24 | 12 | 0 | 0 | 0% | 24 | 66.67% | 33.33% | 0% | 66.67% | June 2020
474 | 150159- Promotion of Social Forestry Through Community Participation in SWA. (A)/FDWP/09.08.2015 | 120 | 42.816 | 33.153 | 0 | 0 | 0% | 42.816 | 35.68% | 27.63% | 0% | 35.68% | Beyond June 2020
TOTAL ON-GOING SCHEMES |  | 651.803 | 433.989 | 89.039 | 2.263 | 0 | 0% | 433.989 | 66.58% | 13.66% | 0% | 66.58%
NEW SCHEMES FOREST | [7 empty] | 0
483 | 190035-Green Growth intiative for South Waziristan District. (B) | 35 | 0 | 15 | 0 | 0 | 0% | 0 | 0% | 42.86% | 0% | 0% | Beyond June 2020
TOTAL FORESTRY |  | 686.803 | 433.989 | 104.039 |  |  | 0% | 433.989 | 63.19% | 15.15% | 0% | 63.19%
FORESTRY (Sericulture/NTFP) | [7 empty] | 0
489 | 190343-Promotion of NTFPs in Merged Areas (South) . (B) | 75 | 0 | 10 | 0 | 0 | 0% | 0 | 0% | 13.33% | 0% | 166.3% | Beyond June 2020
TOTAL FORESTRY SERICULTURE / NTFP |  | 761.803 | 433.989 | 114.039 | 0 | 0 | 0% | 433.989 | 0% | 14.97% | 0% | 3.172%
HEALTH (Basic) | [7 empty] | 0
493 | 160466-Public Private Partnership for Operationalization of Model hospital Sholam SWA (R) | 309.449 | 245.709 | 50 | 23.788 | 47.576 | 200% | 293.285 |  |  |  | 94.78%
497 | 130474- Opening of 18 CHCs/ CDs in SWA. ® | 144.689 | 124.689 | 20 | 0 | 0 | 0% | 124.689 | 86.18% | 13.82% | 0% | 86.18% | June 2020 | Salaries paid to staff
500 | 140317-Estab: of 01-No Category D Hospital with two specialties at Makin, Impr: & Rehab: of 04-Nos existing health facilities in Mehsud closed area (Umbrella) (B) | 158.101 | 24.162 | 10 | 0 | 0 | 0% | 24.162 | 15.28% | 6.325% | 0% | 15.28% | Beyond June 2020 | Work in progress, Work stopped due to could weather.
515 | 150172- Rehabilitation of Existing Health Facilities including Civil Hospital Sararogha, SWA (A)/FDWP/26.01.2016 | 83.925 | 34.479 | 2.9 | 0 | 0 | 0% | 34.479 | 41.08% | 3.455% | 0% | 41.08% | Beyond June 2020 | Work in progress.
525 | 110271-Upgradation of 04 No’s CDs to CHCs Level in SW Agency (A)/FDWP/23.04.2013 | 53.41 | 32.987 | 3 | 0 | 0 | 0% | 32.987 | 61.76% | 5.617% | 0% | 61.76% | Beyond June 2020
528 | 150392-Establishment of 04 CHCs and Up gradation of 11 CDs to CHCs in SWA (Umbrella) (ADP No. 235/140315)(B) | 176.072 | 18.8 | 5 | 0 | 0 | 0% | 18.8 | 10.68% | 2.84% | 0% | 10.68% | Beyond June 2020
531 | 140316-Estab: of 01-No Category D Hopital at at Thanak / Narra & and Const: of 04-Nos Labour suits and provision of 19-Nos residentail facilities to staff in existing health facilities (Umbrella) (A)/FDWP/30.11.2016 | 199.727 | 114.367 | 10 | 0 | 0 | 0% | 114.367 | 57.26% | 5.007% | 0% | 57.26% | Beyond June 2020
534 | 130018- Solarization of Existing Health Facilities in SWA.(A)/FDWP/03-04-2014 | 33.534 | 14 | 19.534 | 4.884 | 1.83 | 37.47% | 15.83 | 41.75% | 58.25% | 9.368% | 47.21% | June 2020
540 | 140250- Solarization of 08 Existing facilities in closed area, SWA. (A)/ ADSC/12.08.2014 | 10.404 | 0 | 7.404 | 0 | 0 | 0% | 0 | #VALUE! | #VALUE! | 0% | #VALUE! | Beyond June 2020
541 | 150391-Estab: / Up-gradation of existing HFs to CHUs in District South Waziristan (B) | 150 | 0 | 33.91 | 0 | 0 | 0% | 0 | 0% | 22.61% | 0% | 0% | Beyond June 2020
542 | 110270-Establishment of 19 No’s CHCs in SWA (A)/FDWP/08.04.2013 | 197.717 | 150.564 | 6 | 0 | 0 | 0% | 150.564 | 76.15% | 3.035% | 0% | 76.15% | Beyond June 2020
GANT TOTAL HEALTH DEPTT: |  | 1197.175 | 514.048 | 117.748 | 4.884 | 1.83 | 0% | 515.878 | 42.94% | 9.835% | 1.554% | 43.09%
HIGHER EDUCATION | [7 empty] | 0
568 | 070200-Const: of 2 No’s Hostels (one for students & one for teacher) and provision of missing facilities in Government Degree College Wana, SWA (Revised) (A)/FDWP/28-02-2013 | 128.95 | 110.95 | 11.419 | 0 | 0 | 0% | 110.95 | 86.04% | 8.855% | 0% | 86.04% | Beyond June 2020
TOTAL ON-GOING SCHEMES HIGHER EDUCATION DEPT: |  | 128.95 | 110.95 | 11.419 | 0 | 0 | 0% | 110.95 | 86.04% | 8.855% | 0% | 86.04%
GRANT TOTAL HIGHER EDUCATION DEPT: | [6 empty] | 0% | 0 | 0% | 0% | 0% | 0%
LOCAL GOVT. LG&RDD, DEPT: | [7 empty] | 0
612 | 180106-Execution of Rural Works Program in District SW (B) | 64.335 | 0 | 9.828 | 0 | 0 | 0% | 0 | 0% | 15.28% | 0% | 0% | Beyond June 2020
626 | 160057-Execution of Rural Work Programme in SWA (A)/FDWP/09.03.2017 | 77.9 | 65.137 | 12.763 | 3.191 | 0 | 0% | 65.137 | 83.62% | 16.38% | 0% | 83.62% | June 2020
629 | 140343-Execuction of Rural Works Programmes (2010-13) in SWA (Umbrella) (A)/FDWP/18.10.2016 | 65.1 | 51.994 | 13.106 | 3.277 | 0 | 0% | 51.994 | 79.87% | 20.13% | 0% | 79.87% | June 2020
640 | 170313-Rural Works Programme in SWA (B) | 75 | 0 | 10 | 0 | 0 | 0% | 0 | 0% | 13.33% | 0% | 0% | Beyond June 2020
TOTAL ON - GOING SCHEMES LOCAL GOVT. |  | 282.335 | 117.131 | 45.697 | 6.468 | 0 | 0% | 117.131 | 41.49% | 16.19% | 0% | 41.49%
NEW SCHEMES LOCAL GOVT. LG&RDD | [7 empty] | 0
653 | 190309-PCC Link Roads & Drinking Water Supply Schemes in South Waziristan. (B) | 40 | 0 | 12.185 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
GRANT TOTAL LOCAL GOVT. |  | 322.335 | 117.131 | 57.882 | 6.468 | 0 | 0% |  | 0% | 0% | 0% | 0%
MULTI SECTORAL DEVELOPMENT
657 | 170315- Special Development Package For Remote and Neglected Areas in SWA (B) | 150 | 0 | 30 | 0 | 0 | 0% | 0 | 0% | 20% | 0% | 0% | Beyond June 2020
660 | 160058-Special Development Package for recently opened area TDPs Return areas in SWA (A)/FDWP/ 09.03.2017 | 195.7 | 118.709 | 30 | 0 | 0 | 0% | 118.709 | 60.66% | 15.33% | 0% | 60.66% | Beyond June 2020
662 | 080190-Special Grant for Development Schemes in Tehsil Toi Khullah of South Waziristan Agency (GD) (A)/FDWP/07-11-2007 | 173.077 | 72.008 | 11.51 | 0 | 0 | 0% | 72.008 | 41.6% | 6.65% | 0% | 41.6% | Beyond June 2020
663 | 050018-Special Development Package for Tehsil Toi Khullah of SWA (R) (GD)/ (A)/FDWP/24.11.2009 | 192.358 | 123.397 | 4 | 0 | 0 | #DIV/0! | 123.397 | 64.15% | 2.079% | 0% | 64.15% | Beyond June 2020
668 | 150082-Intergrated Area Development Progam, South Waziristan Agency, (A) / FDC/11-04-2016 | 298.84 | 231.094 | 35 | 0 | 0 | 0% | 231.094 | 77.33% | 11.71% | 0% | 77.33% | Beyond June 2020
670 | 040090-Special Development Package for Shaktoi & Shobi Khel area of Tehsil Ladha of SWA (GD) (A)/FDWP/ 02-12-2006 | 93.318 | 83.943 | 9.375 | 0 | 0 | 0% | 83.943 | 89.95% | 10.05% | 0% | 89.95% | Beyond June 2020
672 | 990098-Development Packages for Manitoi & Santoi areas of South Waziristan Agency (R) (A)/FDWP/ 25-03-2011 | 198.193 | 104.657 | 4 | 0 | 0 | 0% | 104.657 | 52.81% | 2.018% | 0% | 52.81% | Beyond June 2020
681 | 010130-Development Package for Shawal in accessible are of SWA (A)/FDWP/ 20.10.2008 | 151.595 | 102.275 | 6 | 0 | 0 | 0% | 102.275 | 67.47% | 3.958% | 0% | 67.47% | Beyond June 2020
TOTAL MULTI SECTORAL DEV: |  | 1453.081 | 836.083 | 129.885 | 0 | 0 | 0% | 836.083 | 57.54% | 8.939% | 0% | 57.54%
NEW SCHEMES MULTI SECTOR DEV:
685 | 190347-Special Integrated area Development Package for South Waziristan (B) | 200 | 0 | 100 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
GRANT TOTAL OF MULTI SCETOR |  | 1653.081 | 836.083 | 229.885 | 0 | 0 | 0% |  | 0% | 0% | 0% | 0%
ROADS DEPARTMENT
712 | 150178- Construction of BT Roads in Sarwekai & Wana Sub Division in SWA. (A)FDWP/23.02.2016 | 194.83 | 181.3 | 4.83 | 0 | 0 | 0% | 181.3 | 93.06% | 2.479% | 0% | 93.06% | Beyond June 2020
713 | 140332- Construction of Road from Shahoor to Toormandi via Pastai Khawazai 10 Kms in SWA. (Umbrella) (A)/FDWP/31.05.2016 | 177.326 | 142 | 10.326 | 0 | 0 | 0% | 142 | 80.08% | 5.823% | 0% | 80.08% | Beyond June 2020
714 | 140336- Construction of 5 Kms BT Roads in SWA. ( Umbrella) ( B) | 80.548 | 60.2 | 20.348 | 16.459 | 15.444 | 93.83% | 75.644 | 74.74% | 25.26% | 75.9% | 93.91% | June 2019
716 | 160048-Construction of BT Road in Sarwekai and in Wana Sub-Division SWA (A)/FDWP/10.01.2017 | 155 | 125.796 | 29.204 | 7.301 | 4.722 | 64.68% | 130.518 | 81.16% | 18.84% | 16.17% | 84.21% | June 2019
731 | 140030-Const: of BT Road from Siplatoi to Nano via Aghbargai Ph-II (10-Kms) in SWA (Umbrella) (A)/FDWP/31.05.2016 | 100.022 | 71.576 | 20 | 0 | 0 | 0% | 71.576 | 71.56% | 20% | 0% | 71.56% | Beyond June 2020
732 | 160049-Rehabilitation of Existing Road in SWA (A)/FDWP/10.01.2017 | 199.185 | 154.783 | 10.402 | 0 | 0 | 0% | 154.783 | 77.71% | 5.222% | 0% | 77.71% | Beyond June 2020
734 | 140329- Black Topping of 8 Kms Road in SWA (Umbrella) ( B) | 144 | 0 | 0.5 | 0 | 0 | 0% | 0 | 0% | 0.3472% | 0% | 0% | Beyond June 2020
736 | 140323-Impt:, Widening & Rehab: of 12-KMs existing road in Mehsud closed area (B) | 180 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2778% | 0% | 0% | Beyond June 2020
738 | 140331 –Black Topping of Toormandi to Spinkai Raghzai via Chagmalai 10 Kms Phase II in SWA. (Umbrella) (B) | 180 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2778% | 0% | 0% | Beyond June 2020
739 | 140337-Construction of BT Road from Shahoor Toor Mandi Phase II (6-Km) in SW (Umbrella) (A) / FDWP/10.01.2017 | 104.089 | 74.7 | 29.389 | 7.347 | 2.511 | 34.18% | 77.211 | 71.77% | 28.23% | 8.544% | 74.18% | June 2020
741 | 140333- Construction of Road from Kotkai to Stara Panga via Ganderai 10 Kms in SWA (Umbrella) (A)/FDWP/16.06.2015 | 131.189 | 0 | 8.001 | 0 | 0 | #DIV/0! | 0 | 0% | 6.099% | 0% | 0% | Beyond June 2020
742 | 140338- Construction of BT Road from Sam Masap Mela, Mehsta to Dera Malik Shai Area ( 19 Kms) Phase I in SWA (Umbrella) ( B) | 190 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2632% | 0% | 0% | Beyond June 2020
743 | 140271- Construction of 03 Kms Roads in Ladha Sub- Division (Closed Area) SWA ( B) | 51.197 | 38.2 | 12.997 | 12.997 | 6.199 | 47.7% | 44.399 | 74.61% | 25.39% | 47.7% | 86.72% | June 2019
744 | 140072-Construction of Shingle Roads of Different lengths in District SW (20-Kms) (Umbrella) (B) | 144 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.3472% | 0% | 0% | Beyond June 2020
745 | 140135- Const: of Road from Gulzaman Narai to Bazid Narai via Borakai ( 10 KMs) in SWA. ( Umbrella) (B) | 179.375 | 25 | 10 | 0 | 0 | 0% | 25 | 13.94% | 5.575% | 0% | 13.94% | Beyond June 2020
746 | 140143- BT Road from Ladha to Ghowak ( 5 Kms) & Widening / BT Road from Sam to Kareeb Korrona Lower Kanigurram in SWA (Umbrella) (A)/FDWP/10.01.2017 | 156.685 | 88 | 10 | 0 | 0 | 0% | 88 | 56.16% | 6.382% | 0% | 56.16% | Beyond June 2020
747 | 140061- Const: of Link Road to Lower & Upper Kanigurram Baba Sir to Salarogha ( 4.5 Kms) & Const: of 5 KMs BT Road ( Bazai to Tangi Budinzai up to Larima with link Road to Ladha Patwalai Road 5 Kms ) in SWA (Umbrella) (A)/FDWP/10.01.2017 | 168.502 | 57.57 | 10 | 0 | 0 | #DIV/0! | 57.57 | 34.17% | 5.935% | 0% | 34.17% | Beyond June 2020
750 | 140184-Construction of 10 KMs BT Road (Balance Length of Badar Mantoi Shakai BT Road 10 KMs in District South Waziristan (Umbrella) (B) | 207.718 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2407% | 0% | 0% | Beyond June 2020
751 | 140162-Construction of Ghundakai Sarina Road in District South Waziristan (10KMS) (Umbrella) (B) | 180 | 0 | 0.5 | 0 | 0 | 0% | 0 | 0% | 0.2778% | 0% | 0% | Beyond June 2020
752 | 140190-Construction of BT Road from Sam Masap Mela Meshta Dara Malik Shai area Phase II (10 KMs ) in District SW Umbrella (B) | 180 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2778% | 0% | 0% | Beyond June 2020
763 | 170296-Construction of BT Road from Mantoi Jirga Ground via Ghunda Kai Village via Matter Jan to Nika Ziarat area (6-Km) in SWA (A)/ FDWP / 01. 01.2018 | 99.9 | 30.978 | 17.737 | 0 | 0 | 0% | 30.978 | 31.01% | 17.75% | 0% | 31.01% | Beyond June 2020
764 | 170302-Construction of BT road in Ladha SWA (A)/FDWP/01.01.2018 | 184.436 | 95.459 | 25 | 0 | 0 | 0% | 95.459 | 51.76% | 13.55% | 0% | 51.76% | Beyond June 2020
765 | 170303-Construction of BT road in Sarwekai Sub Division , SWA (A)/FDC/07.02.2018 | 351.326 | 4 | 11.499 | 0 | 0 | 0% | 4 | 1.139% | 3.273% | 0% | 1.139% | Beyond June 2020
766 | 170304-M&R / Rehabilitation of Existing roads in Sarwakai & Wana Sub Division SWA (B) | 90 | 0 | 3.0 | 0 | 0 | 0% | 0 | 0% | #VALUE! | #VALUE! | 0% | Beyond June 2020
767 | 170305-M&R Rehabilitation of Existing roads in Ladha Sub Division SWA (B) | 90 | 0 | 3 | 0 | 0 | #DIV/0! | 0 | 0% | 3.333% | 0% | 0% | Beyond June 2020
769 | 170392-Construction of BT road in Wana Sub Division SWA (A)/FDWP/01.01.2018 | 109.453 | 28.567 | 10 | 0 | 0 | 0% | 28.567 | 26.1% | 9.136% | 0% | 26.1% | Beyond June 2020
774 | 140324-Construction of 11 Km B /T road (03 No’s in SWA) (Umbrella) (A)FDWP/19.04.2017 | 198.437 | 127.2 | 18 | 0 | 0 | 0% | 127.2 | 64.1% | 9.071% | 0% | 64.1% | Beyond June 2020
775 | 160476-Construction of BT Road Village Ghawa Khawa Tehsil Wana (SWA) (5-Kms) A/FDWP/16.02.2017 | 68.907 | 54.907 | 14 | 0 | 0 | 0% | 54.907 | 79.68% | 20.32% | 0% | 79.68% | June 2020
776 | 150177-Construction of BT Roads In Ladha Sub Division in SW (A) /FDWP /23.02.2016 | 198.819 | 195.819 | 3 | 3 | 0 | 0% | 195.819 | 98.49% | 1.509% | 0% | 98.49% | June 2020
777 | 140321-Cosntruction of 06 KM BT Road and Rehabilitation of 5.5 Km road in Mehsud closed area (B) | 149 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.3356% | 0% | 0% | Beyond June 2020
779 | 140334-- Black Topping of Roads in SW, Phase II (25 Kms) ( Umbrella) (B) | 190 | 0 | 0.5 | 0 | 0 | #DIV/0! | 0 | 0% | 0.2632% | 0% | 0% | Beyond June 2020
780 | 140322-Const: of 16-KMs B/T Road in SWA (A)/FDWP/31.05.2016 | 453.804 | 105.207 | 13.505 | 0 | 0 | 0% | 105.207 | 23.18% | 2.976% | 0% | 23.18% | Beyond June 2020
781 | 160047-Construction of BT Road in Ladha Sub-Division SWA (A)/FDWP/10.01.2017 | 142.057 | 130.533 | 11.524 | 0 | 0 | 0% | 130.533 | 91.89% | 8.112% | 0% | 91.89% | June 2020
788 | 180095-Constructon of BT Road in Ladha District in SW (B) | 148.776 | 0 | 10 | 0 | 0 | 0% | 0 | 0% | 6.722% | 0% | 0% | Beyond June 2020
789 | 180096-Construction of BT Road in Sarwekai District in SW (B) | 149.324 | 0 | 10 | 0 | 0 | #DIV/0! | 0 | 0% | 6.697% | 0% | 0% | Beyond June 2020
790 | 180097-Cosntruction of BT Road in Wana District SW (B) | 188.468 | 0 | 3 | 0 | 0 | #DIV/0! | 0 | 0% | 1.592% | 0% | 0% | Beyond June 2020
804 | 170438-Construction of Link road from Jandola Gabbar Road to Mais Khan Koroona Smal area Tehsil Ladha (15-Km) Phase –I (A) /FDWP/17.04.2018 | 247.138 | 0 | 20 | 0 | 0 | 0% | 0 | 0% | 8.093% | 0% | 0% | Beyond June 2020
807 | 170427-Construction of 07 Km B /T road Chalghoza forest village Ghurlana Tehsil Birmal SWA (A)/FDWP/ 01. 01. 2018 | 107.4 | 45 | 25 | 0 | 0 | 0% | 45 | 41.9% | 23.28% | 0% | 41.9% | Beyond June 2020
808 | 170439- Construction of shingle track SWA (A/ FDWP/ 20/09/2017 | 96.34 | 0 | 11.057 | 0 | 0 | #DIV/0! | 0 | 0% | 11.48% | 0% | 0% | Beyond June 2020
818 | 180577-Rehabilitation of existing roads in District South Wazirista (A)/ PDWP/22.04.2019 | 52 | 0 | 10 | 0 | 0 | #DIV/0! | 0 | 0% | 19.23% | 0% | 0% | Beyond June 2020
TOTAL ON - ONGOING SCHEMES ROADS |  | 6419.251 | 1836.795 | 396.819 | 47.104 | 28.876 | 61.3% | 1865.671 | 28.61% | 6.182% | 7.277% | 0%
NEW SCHEMES ROADS
825 | 190260- Constrcution of Black Topped Roads in Tribal District South Waziristan (B) | 160 | 0 | 40.605 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
829 | 190327-Construction of Dashka to Razin Haris Koroona Tehsil Makin District South Waziristan (B) | 180 | 0 | 10 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
TOTAL OF NEW SCHEMES ROADS |  | 340 | 0 | 50.605 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0%
GANT TOTAL OF ROADS |  | 6759.251 | 1836.795 | 447.424 | 47.104 | 28.876 | 0% | 1865.671 | 0% | 0% | 0% | 0%
835 | 150147-Design & Rehabilitation of Damaged Portions of Roads in SWA (Phase - II), Gomal Zam Wana Road. (Km 66 to Km 117) (A)/FDWP/23/02/2016 | 95.384 | 89.224 | 4.16 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
TOTAL ONGOING SCHEME OF ROADS AND BRIDGES (PROVINCIAL) |  | 95.384 | 89.224 | 4.16 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0%
SOCIAL WELFARE DEPT:
862 | 170319-Provision of Equipments to Special Persons and Purchase of Swing Machines Whell Chairs & Crutches for Distribution among deserving Person in SWA (R) | 19.741 | 0 | 17.741 | 0 | 0 | 0% | 0 | 0% | 89.87% | 0% | 0% | Beyond June 2020
GRANT TOTAL SOCIAL WELFARE |  | 19.741 | 0 | 17.741 | 0 | 0 | 0% | 0 | 0% | 89.87% | 0% | 0%
SPORTS DEPT:
873 | 180536-Promotion of Culture & Sports Activities in District SW (A)/DDWP/20-02-2019 | 31.25 | 8.112 | 23.138 | 0 | 0 | #DIV/0! | 8.112 | 25.96% | 74.04% | 0% | 25.96% | Beyond June 2020
883 | 180111-Rehaib Construction of Sports Facilities in District SW (A)/PDWP/22-04-2019. | 250.178 | 13.333 | 11.888 | 0 | 0 | 0% | 0 | 5.329% | 4.752% | 0% | 0% | Beyond June 2020
TOTAL SPORTS ONGOING SCHEMES |  | 281.428 | 21.445 | 35.026 | 0 | 0 | 0% | 8.112 | 7.62% | 12.45% | 0% | 2.882%
GRANT TOTAL SPORTS DEPT: | [6 empty] | 0% | #REF! | 0% | 0% | 0% | #REF!
URBAN DEVELOPMENT
931 | 170314-Provision of Municipal Services in Wana and Makin District SW (A)/DDWP/27-05-2019 | 77.55 | 0 | 50.697 | 0 | 0 | 0% | 0 | 0% | 65.37% | 0% | 0% | Beyond June 2020
935 | 170404-Provision of Municipal Service / Civic Admenties in Major Towns of South Tribal District | 466.721 | 122.739 | 25 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
937 | 180105-Municipal Services and Commercial area Development in District South Waziristan Tribal District (B) | 90 | 0 | 14.48 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
TOTAL ON GOING SCHEMES URBAN DEV: |  | 634.271 | 122.739 | 90.177 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0%
GRANT TOTAL URBAN DEVELOPMENT | [6 empty] | 0% | #REF! | 0% | 0% | 0% | 0%
WATER
963 | 140328-Construction of 43 Protection Bunds, Const: of 6 Check Dams, Const: of 300 Meters Flood Protection Walls, Rehab: of 500 Meters Major Irrigation Channels & Installation of 11 Micro HP in SWA | 150 | 92.116 | 4.451 | 4.451 | 3.217 | 72.28% | 92.116 | 61.41% | 2.967% | 100% | 61.41%
971 | 170316-Construction of Irrigation Channels and Rehabilitation of Existing Irrigation in SWA (A)/FDWP/24-01-2018 | 89.998 | 64.206 | 25.792 | 5.448 | 5.448 | 100% | 69.654 | 71.34% | 28.66% | 21.12% | 77.4% | June 2020
972 | 170317-Construction of Micro Hydle Power units in SWA (A)/FDWP/24.01.2018 | 47.6 | 38.6 | 9 | 2.25 | 1.437 | 63.87% | 40.037 | 81.09% | 18.91% | 15.97% | 84.11% | June 2020
973 | 170318-Construction of Small Check Dams and Flood Protection Walls / Works in SWA (A)/DDWP/10-05-2019 | 40 | 0 | 23.052 | 0 | 0 | #DIV/0! | 0 | 0% | 57.63% | 0% | 0% | Beyond June 2020
977 | 170412-Construction / Installation of Micro Hydle Power Project in SWA (B) | 10.6 | 8.465 | 2.135 | 2.135 | 2.135 | 100% | 10.6 | 79.86% | 20.14% | 100% | 100% | June 2020
999 | 180108-Construction of Irrigation Channel in District SW (A)/DDWP/10-05-2019 | 80.485 | 0 | 26.242 | 0 | 0 | #DIV/0! | 0 | 0% | 32.6% | 0% | 0% | Beyond June 2020
1000 | 180109-Construction of Micro Hudle Power Units Check Dams in District SW (A)/DDWP/10-05-2019 | 74 | 0 | 29.774 | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | Beyond June 2020
GRANT TOTAL WATER |  | 342.683 | 111.271 | 115.995 | 9.833 | 9.02 | 0% | 0 | 0% | 0% | 0% | 0%