## ADP Schemes1
S.No | Facilities with scheme code and ADP No. | Status | Source | Approved cost | Expenditure up to 30/06/2019 | Physicial achievement up to 30/06/2019 | Financial achievement up to 30/06/2019 | Physical Targets | Physical achievement | ADP Allocation for CFY | Release (CFY) | Utilization % (CFY) | Utilization since commencement | Achievement since commencement
|  |  |  | Rs, |  |  |  | % (CFY) | % (CFY)
1 | 872/180529 | (A) |  | 25.0M | 10.338M | 100% | 100% | Events:36 | Nil | 14.662 | 3.734M | Nil | 42% | Events:18
| Promotion of Culture and Sports Activities in District Bajaur. |  |  |  |  | Events: 15 |  | Provision of Sports Goods : | [5 empty] | Sports Goods:
[6 empty] | Provision of Sports Goods: 126 Clubs |  | 200 Clubs | [5 empty] | 126Cubs.
MONTHLY PROGRESS REPORT OF LIVESTOCK & DAIRY DEVELOPMENT TRIBAL DISTRICT BAJAUR UNDER ADP 2019-20
FOR THE MONTH OF 12/2019
S.# | ADP General S.No | Name of ADP Schemes | ADP.Provision for 2019-20 (in Million) | Exp: last FY year 2018-19 30/6/2019 | Current year Release 2019-20 |  |  |  | Expenditure during CFY for the month 12/2019 |  |  | Progressive Expenditure from 1-7-2019 up to 12/2019 |  |  | financial %age | Phy: Target | Physical Achievement | Remarks
[5 empty] | Cap | Rev | Total |  | Cap | Rev | Tot | Cap | Rev | Tot
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | 82 | 070103-Opening of 5-CVDs 5-CVCs 6-AICs an Upgradation of 2-CVDs to CVHs Status in Bajaur Agency.(R) | 0 | 18.958 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Animal to be Targeted=40000 | Animal to be Targeted=20066
[16 empty] | Bird to be Vaccinated=120000 | Bird to be Vaccinated=66501
[16 empty] | Animal to be Vaccinated=50000 | Animal to be Vaccinated=34627
[16 empty] | Animal to be Inseminated=10000 | Animal to be Inseminated=3818
2 | 81 | 090012-Provision of Mobile Vety: Clinic in Bajaur Agency Status ( R ) | 0 | 4.5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Animal to be Targeted=10000 | Animal to be Targeted=11557
[16 empty] | Bird to be Vaccinated=70000 | Bird to be Vaccinated=34000
[16 empty] | Animal to be Vaccinated=30000 | Animal to beVaccinated=31500
[16 empty] | Animal to be Inseminated=900 | Animal to be Inseminated=980
3 | 43 | 110042-Establishment of Vety: Diagnostic Laboratory in CVH Khar & Construction of Garrage for 02 vehicles in ALO Office Bajaur Agency ( R ) | 0 | 2.225 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tested to be Performed=3800 | Tested to be Performed= 1807
4 | 52 | 170021-Provision of Medicine and Artificial Insemination Services in Existing Veterinary Institutions in Bajaur Agency (A) | 0 | 12.892 | 0 | 4.33 | 4.33 |  | 0 | 0.055 | 0.055 | 0 | 4.33 | 4.33 | 100% | Animals to be Inseminated=6000 | Animals to be Inseminated=2666
[16 empty] | Animals to be Targeted=9000 | Animals to be Targeted=8668
5 | 64 | 180066-Rehabilitation and Reconstruction of 04 Vety: Centers & Strengthening of existing Veterinary facilities in District Bajaur (A) | 0 | 6.15 | 0 | 1.292 | 1.292 |  | 0 | 0.05 | 0.05 | 0 | 1.292 | 1.292 | 100% | Animal Spray =10000 | Animal Spray =34850
[16 empty] | Animal Trated Field Day=15000 | Animal Trated Field Day=5247
MONTHLY PROGRESS REPORT FOR THE MONTH OF DECEMBER 2019 (46 NOS SMALL DWSS CIVIL WORK TRIBAL DISTRICT BAJAUR IN RESPECT OF LG& RDD, BAJAUR FOR THE YEAR 2019-20.
S.No. | Name of scheme | Tender below Bore cost | Tender below Water Tank cost | Solarization cost | Total cost | Contractor offered Rate | Expenditure | Financial % | Physical % | Scope of Work | Ongoing | Completed | NYS | Date of work order | Remarks
1 | DWSS Low cost Solar Based at Alizai. Qadar Khan. | 0.42493 | 0.1378 | 0.543 |  | 45.10% Abdul Hameed Khan |  |  | 15: Work in progress
2 | DWSS Low cost Solar Based at Haji Lawang. Gul Hameed Jan | 0.31732 | 0.1378 | 0.4346 |  | -do-
3 | DWSS Low cost Solar Based at Shindai Morr Tehsil Khar. | 0.31732 | 0.1378 | 0.4346 |  | -do-
4 | DWSS Low cost Solar Based at Matiullah Korona Khar. | 0.31732 | 0.1378 | 0.4346 |  | -do-
5 | Installation of Solar System with over head Water Tank on existing well at Loi Jowar. | 0 | 0.1378 | 0.543 |  | -do-
6 | DWSS Low cost Solar Based at Mohammad Ismail Ghani Addai Tesil Khar. | 0.31732 | 0.1378 | 0.4346 |  | -do-
7 | DWSS Low cost Solar Based at Tehsil Khar.Siraj Akbar Sabir | 0.42493 | 0.1378 | 0.543 |  | -do-
8 | DWSS Low cost Solar Based at Shaikh Baba.Bakht Rawan Balolai Shah Khar | 0.31732 | 0.1378 | 0.4346 |  | -do-
9 | DWSS Low cost Solar Based at Ghundo. Sahib Zada/Sawada Korona | 0.26286 | 0.1378 | 0.543 |  | -do-
10 | DWSS Low cost Solar Based at Kamar Sar.Qaid Rashid Korona | 0.31732 | 0.1378 | 0.4346 |  | -do-
11 | DWSS Low cost Solar Based at Sadiq Abad Pattak.Attaullah Korona | 0.31732 | 0.1378 | 0.4346 |  | -do-
12 | DWSS Low cost Solar Based at Yousaf Abad.Aurangzeb Inqilabi. | 0.31732 | 0.1378 | 0.4346 |  | -do-
13 | DWSS Low cost Solar Based at Tangai.Momin Khan. | 0.31732 | 0.1378 | 0.4346 |  | -do-
14 | DWSS Low cost Solar Based at Shawo.Abdul Qayum Khan S/O Shamsur Rehman | 0.31732 | 0.1378 | 0.4346 |  | -do-
15 | DWSS Low cost Solar Based at Loisam.Fateh Rehman S/O Buzarg. | 0.31732 | 0.1378 | 0.4346 |  | -do-
16 | DWSS Low cost Solar Based at Raghagan Khan Abad. | 0.31732 | 0.1378 | 0.4346 |  | -do-
17 | DWSS Low Cost Solar Based at Pashat Killi. | 0.44968 | 0.1456 | 0.4346 |  | 44%Alam Zeb & Sons
18 | DWSS Low Cost Solar Based at Lako. | 0.44968 | 0.1456 | 0.4346 |  | -do-
19 | DWSS Low Cost Solar Based at Bar Trass. | 0.45024 | 0.1456 | 0.543 |  | -do-
20 | DWSS Low Cost Solar Based at Tabai. | 0.45024 | 0.1456 | 0.543 |  | -do-
21 | DWSS Low Cost Solar Based at Rasha Dherai. | 0.44968 | 0.1456 | 0.4346 |  | -do-
22 | DWSS Low Cost Solar Based at Gulo Shah. | 0.44968 | 0.1456 | 0.4346 |  | -do-
23 | Installation of solar system with Surface Water Tanks at Shukrata. | 0.32368 | 0.14056 | 0.4346 |  | -do-
24 | DWSS Low Cost Solar Based at Batmalai. | 0.44968 | 0.1456 | 0.4346 |  | -do-
25 | DWSS Low Cost Solar Based at Chinargo Pashat. | 0.44968 | 0.1456 | 0.4346 |  | -do-
26 | DWSS Low Cost Solar Based at Charmang. | 0.51048 | 0.17987 | 0.543 |  | Jamal & Builders 35.30 % below
27 | DWSS Low Cost Solar Based at Nakhtar. | 0.51048 | 0.17987 | 0.543 |  | -do-
28 | Construction of Low cost DWSS Solar Based at Parmakhai Nawagai Shago, Open Well existing. | 0.35585 | 0.17987 | 0.38 |  | -do-
29 | DWSS Low Cost Solar Based at Manogai. | 0.51038 | 0.16563 | 0.4346 |  | -do-
30 | DWSS Low Cost Solar Based at Agra. | 0.50589 | 0.1638 | 0.4346 |  | 37% belowAbdul Hameed
31 | Construction of 2 Nos Installatin of Solarization with 02 Nos Water Tanks on existing Bore at Zaga Dherai. | 0 | 0.3276 | 0.76055 |  | -do-
32 | DWSS Low Cost Solar Based at Shahi Tangi. | 0.50589 | 0.1638 | 0.4346 |  | -do-
33 | DWSS Low Cost Solar Based at Bakaro Shah. | 0.50589 | 0.1638 | 0.4346 |  | -do-
34 | DWSS Low Cost Solar Based at Ghakhi. | 0.31311 | 0.1638 | 0.54325 |  | -do-
35 | DWSS Low Cost Solar Based at Tarkho. | 0.31331 | 0.1638 | 0.54325 |  | -do-
36 | DWSS Low Cost Solar Based at Bar Mego. | 0.35469 | 0.1638 | 0.54325 |  | -do-
37 | DWSS Low Cost Solar Based at Garigal. | 0.50589 | 0.1638 | 0.4346 |  | -do-
38 | DWSS Low Cost Solar Based at Shakro. | 0.50589 | 0.1638 | 0.4346 |  | -do-
39 | DWSS Low Cost Solar Based at village Hafizabad Malangi Tehsil Loi Mamund. | 0.50589 | 0.1638 | 0.54325 |  | -do-
40 | DWSS Low Cost Solar Based at Bara Shah Irab Mamund. | 0.50589 | 0.1638 | 0.54325 |  | -do-
41 | DWSS Low Cost Solar Based at Gatkai (Centre) | 0.50589 | 0.1638 | 0.4346 |  | -do-
42 | DWSS Low Cost Solar Based at Mulyano Cham Zarai. | 0.3528 | 0.17514 | 0.38 |  | -do-
43 | DWSS Low Cost Solar Based at Barang. | 0.51392 | 0.2432 | 0.543 |  | 36% Malik Hazrat Gul
44 | DWSS Low Cost Solar Based at Shamozai. | 0.51392 | 0.2464 | 0.543 |  | -do-
45 | DWSS Low Cost Solar Based at Murdara. | 0.37632 | 0.2464 | 0.543 |  | -do-
46 | Installation of Solar System on with surface water Tanks on existing well at Shamozai Darra. | 0.37632 | 0.2464 | 0.543 |  | -do-
| Total:- | 17.8915 | 7.5023 | 22.0524 | 64.857
| Add cost of Resistivity Test |  |  |  | 1.301
| Add 0.5% contingency |  |  |  | 0.342
| Add advertisement charges |  |  |  | 0.25
66.75
ON- Going Schemes
S.No | ADP NO # (2019-20) | Name of scheme
| 203/170009 | Construction of Solar Based Drinking Water Supply Schemes in Tribal District Bajaur
1 | do | Gorgoray Barang
2 | do | Tarrala Salarzai
3 | do | Lower Balamkhar Salarzai
4 | do | Bara Lagharray Mamund
5 | do | Malangai Mamund
6 | do | Inayat Kallay Bypass Korona
ON- Going Schemes
S.No | ADP NO (2017-18) | Name of scheme
| 205/170011 | Impovement, Rehabilatation AND Solarization of Existing and Pumping AND Gravity Based DWSS in Tribal District Bajaur.
1 | do | Barkhalozo Mamund
2 | do | Inzari Khar
3 | do | Naig Mamund
4 | do | Tangi Adda Charmung
5 | do | Rai Charmung
6 | do | Bara Nawagai
7 | do | Talai Salarzai
8 | do | Mamenzo Khar
9 | do | Barani Kandaro 1 &2
10 | do | Raghagaan
11 | do | Sadiq Abad Pathak
12 | do | Plang Dag Ghani Adda AND Takhat
ON- Going Schemes
S.No | ADP NO | Name of scheme
| 253/170332 2019-20 | Solarization of Existing and Construction of New Solar Based DWSS in Tribal Merged Area. (All FATA)
1 | do | DWSS Babarra Zyarath kally
2 | do | DWSS Zor Bandar Khar
3 | do | DWSS Bilal Abad Khar
4 | do | DWSS kotkai Charmung
5 | do | DWSS Nway Kalay khar
6 | do | DWSS Commerece College Nary Qilla Khar
ON- Going Schemes
S.No | ADP NO | Name of scheme
| 254/170333 2019-20 | Construction of Gravity Based DWSS in North FATA
1 | do | DWSS Loe Kaly Tangi And Kunj Salarzai
2 | do | DWSS loe kharkai Khatako Sha Mamund
3 | do | DWSS Managay Gharshamozai Barang
4 | do | DWSS koz sapary Gharshamozai Barang
5 | do | DWSS Gowatai And Bakaro Mamund
6 | do | DWSS Geelay Mamaund
7 | do | DWSS Agra Mamund
8 | do | DWSS Shakro Mamund
9 | do | DWSS Bara Almazo Shahi Sarwar And Karri Kamar
10 | do | DWSS Jalai Sar Barang
11 | do | DWSS Kohi Moor Barang
12 | do | Dwss Bonday Shah Zone B
13 | do | DWSS Bonday Shah Zone A
14 | do | DWSS Samasai Khar
15 | do | DWSS Dabar Mamud
16 | do | DWSS Garday Gharshahmozay
17 | do | DWSS Rod Barang Area
ON- Going Schemes
S.No | ADP NO | Name of scheme
204/170010 2019-20
1 | do
2 | do
3 | do
4 | do
5 | do
6 | do
7 | do
8 | do
9 | do
10 | do
11 | do
12 | do
13 | do
ON- Going Schemes
S.No | ADP NO | Name of scheme
| 233/180537 2019-20 | Construction, Improvement Rehabilitation of Existing DWSS Pumping /Gravity Based In bajaur
1 | do | DWSS Gatkai Mamund
2 | do | DWSS Lara Sewai Mamund
3 | do | DWSS Landai Mamund
4 | do | DWSS Badano Mamund
5 | do | DWSS Hayatai Utmankhel
6 | do | DWSS Narang Arang Utmankhel
7 | do | DWSS Asghar Charmung Nawagai
8 | do | DWSS Gulshan Abad Arang Utmankhel
9 | do | DWSS Nawagai (REH)
10 | do | DWSS Kotkai Charmung
New Scheme
S.No | ADP NO | Name of scheme
Rehabilitation Solorization of Existing DWSS in Bajaur District
New Scheme
S.No | ADP NO | Name of scheme
Construction of Solar Gravity Based DWSS In District bajaur
1
| MID YEAR REVIEW 2019-20 | [7 empty] | 14: (Financial)
| (District Level ) | [18 empty] | (District Level)
S.No. | ADP. No | Name of Scheme with approal Forum & Date | Cost | AA/TS date | PC-I Date of |  | Expdr: upto L.F.Y | Allocation 2019-20 | 11: Releases 2019-20; 14: Expenditure 2019-20; 17: % Expdr against releases; 18: Progre: expenditure | % Expdr: against cost | Physical Activiites with Units |  | PC-I Scope | Ach: upto LFY | 2019-20 |  | %age | Progressive Achiement | Remarks if any
[5 empty] | Comme-ncment | Comple-tion |  | Cap | Rev | Total | Cap | Rev | Total | Cap | Rev | Total | [7 empty] | Target | Achievment
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
1 | 428 | Afforestation of Takht Barang & Kohimoor watershed in Bajaur(FDWP) | 34.637 | 2016-01-09 | 2016-09-01 | 2020-06-30 | 33.137 | 0 | 1.5 | 1.5 | 0 | 0.382 | 0.382 | 0 | 0.36 | 0.36 | 94.24% | 33.497 | 96.71% | Tubling Nursery | Acre | 1 | 1 | 0 | 0 | - | 1
[20 empty] | Bare-Rooted Nursery | Acre | 1 | 1 | 0 | 0 | 0 | 1
[20 empty] | Farmer Nursery | Unit | 8 | 8 | 0 | 0 | 100% | 8
[20 empty] | Block Plantation | Acre | 1000 | 1000 | 0 | 0 | - | 1000
[20 empty] | 2nfYear Maintenance | Acre | 1000 | 1000 | 0 | 0 | 100% | 1000
|  | i-1/9/2016 | [17 empty] | 3rd Year Maint: of Block Plantation | Acre | 1000 | 0 | 500 | 500 | 100% | 500
[20 empty] | Distribution of plants free of cost. | Nos | 300000 | 100000 | 0 | 0 | - | 100000
2 | 455 | 170023 Integrated Watershed Management in Bajaur Agency | 61.622 | 2017-10-13 | 2017-07-01 | 2021-06-30 | 40.25 | 0 | 20 | 20 | 0 | 5.094 | 5.094 | 0 | 1.508 | 1.508 | 29.6% | 41.758 | 67.76% | Purchase of fruit plants | No | 7250 | 2320 | 4930 | 0 | - | 2320
[20 empty] | Raising of Fruit Orchard | Acre | 50 | 19 | 31 | 0 | - | 19
[20 empty] | Maintenance of Fruit Orchard | Acre | 150 | 3 | 16 | 16 | 100% | 19
|  | FDWP 20/09/2017 | [17 empty] | Tube Nursery. | Acre | 1 | 0.5 | 0.25 | 0.25 | 100% | 0.75
[20 empty] | Block Plantation | Acre | 900 | 900 | 30 | 0 | - | 900
[20 empty] | 1st Year Maintenace | Acre | 900 | 900 | 0 | 0 | - | 900
[20 empty] | 2nd Year Maint: of Block Plantation | Acre | 900 | 0 | 900 | 900 | 100% | 900
[20 empty] | 3rd Year Maint: of Block Plantation | Acre | 900 | 0 | 0 | 0 | 0 | 0
[20 empty] | Establishment charges | No | 2 | 2 | 2 | 2 | 100% | 2
3 | 676 | Integrated Area Development Project | 43.878 | 2016-11-04 | 2016-08-01 | 2018-06-30 | 34.606 | 0 | 5.8 | 5.8 | 0 | 1 | 1 | 0 | 0.336 | 0.336 | 33.6% | 34.942 | 79.63% | Tube Nursery. | Acre | 1 | 1 | 0 | 0 | 0% | 1
[20 empty] | Purchse of Plants | Nos | 220000 | 220000 | 0 | 0 | 0% | 220000
[20 empty] | Block Plantation with 1st Year Maint: | Acre | 1350 | 1175 | 175 | 0 | 0% | 1175
[20 empty] | 2nd Year Maint: of Block Plantation | Acre | 1350 | 1000 | 175 | 175 | 100% | 1175
|  | Total | 140.137 |  |  |  | 107.993 | 0 | 27.3 | 27.3 | 0 | 6.476 | 6.476 | 0 | 2.204 | 2.204 |  | 110.197
Divisional Forest Officer
Bajaur Forest Division
Khar
Divisional Forest Officer
Bajaur Forest Division
Khar